## Sheet1
Date of Request | Priority | Requestor: | Topic: | Additional Details: | Comments | CM Form received | Database Entry
2019-12-13 | High | SUD | Creating Pre-Admit programs for SUD | Workflow allowing to have a section to enter ALOC |  | Yes | Yes
2019-12-13 | High | SUD/MH | Release of information tracking, also to solve integrated care issues. | Study the possibility of using Consent for Access form
2019-12-13 | High | SUD/MH | Onset of service form review, to capture client signatures and print out the release, instead of signing paper and scanning into EHF | Ensure it complies with CRF-42
2019-12-13 | Low | SUD/MH | Notification pollution. Client Alerts. | Need workflow for how old client alert entries are removed and maintained to stay current
2019-12-13 | Medium | Bill McCabe | Diagnostic Tab – order is solely based on Admission date | Requesting to order consistently with other widgets, open first, the closed episodes by admission | Chris McCaulay to research if this can be done easily outside of this committee
2019-12-06 |  | Linda Cosio | Test MH Supervisor Compliance Report Review | Assessment date runs from last assessment date, not Admission making it appear in compliance when it is actually late. | Draft is done. Testing needs to be completed.
|  | Cybele Lolley | TEST MH Supervisor Compliance Report | Complete testing of report to move into production. | Draft is done. Testing needs to be completed.
2019-12-10 |  | Cybele Lolley | Building NOABD letter & attachment forms into Avatar (English and Spanish). Total 31 | There have been several provider requests to have the NOABD forms in Avatar. Currently in paper form | 1/28/21 - Project to remain. CM Form to be completed. Priority needs to be set.
2019-12-13 |  | SUD | Review documentation requirements as they relate to the use of psychosocial, ALOC or templates in progress notes | Golden Thread Trainings may provide clear guidance. Group can input on training requirements. Dave with work with Karen.
2019-12-13 |  | MH | Revise psychosocial, in particular Trauma and SUD section, and how it relates to the use of CANS-ANSA | Best Practices need to be developed - Childrens
2019-12-13 |  | MH | Update Forms to better support integrating CANS-ANSA into treatment planning, CANS-ANSA report that’s sorted, incorporate scores into Tx Plan. Widget to make it more visible | Creating a widget that shows, last assessment and 2.3 scores | Sent email to Karen asking for input on this. May be resolved by using CDR reports & website.
2019-12-13 |  | SUD | Making ALOC information more visible | Creating a widget that shows last assessment and Dimension scores | Needs to be Defined and Tested
2019-12-27 |  | SUD | Develop a Residential Prior Authorization Request and Decision Form, with routing/alert method & Activity Report | Design a Avatar form to replace the paper form and excel tracking log | Needs workflow modification (start w/ Casey Swank). Need training and implementation support